## DeployTasks DAY1
Step# | Estimated Duration | Node(s) Impacted | Server(s) | Step Details | Step Owner(s) and/or SM9 Group Name
1 | 1hr | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | PREDEPLOYMENT STEP: Take the backup of PROD files and Move required files from stage to SITEA (Will be performed after Code freeze and need not to be included as task in CR). | APP-L2-ECOMM-MIDDLE-TIER
2 | 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | 1) put eccsoa010-12, eccsoa012-01 and eccsoa012-02 in MMode for 30mins 2) Drain eccsoa010-12, eccsoa012-01 and eccsoa012-02 out of service (MT) -go to BIGIPadmin: -search on myacctsvcs.int.westgroup.com -click edit all -take eccsoa010-12, eccsoa012-01 and eccsoa012-02 out of service 3)Execute ./ecomsoa_deploy.sh on siteA(MT) : putty to eccsoa010-12.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts <ENTER> ./ecomsoa_deploy.sh <ENTER> The deploy script will then run and it will take 10-20 minutes to complete. | APP-L2-EBS-DEPLOY
3 | 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | Verify Deployment | APP-L2-ECOMM-MIDDLE-TIER
| 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | (optional) In case of any concerns, Bounce the servers as below: putty to eccsoa010-12.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts/ <ENTER> ./bounceServers.sh myacctsvcs_1000_20070123_prd_eccsoa010-12_1 myacctsvcs_1000_20070123_prd_eccsoa012-01_1 myacctsvcs_1000_20070123_prd_eccsoa012-02_1 <ENTER> | APP-L2-EBS-DEPLOY
5 | 30mins | 1 & 2 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com eccsoa013-06.int.westgroup.com eccsoa013-11.int.westgroup.com eccsoa013-10.int.westgroup.com | 1) Take eccsoa010-12, eccsoa012-01 and eccsoa012-02 out of MMode and put eccsoa013-06 and eccsoa013-11 in MMode for 1 hour 2) swap drains: -go to BIGIPadmin -search on myacctsvcs.int.westgroup.com -click edit all -put eccsoa010-12, eccsoa012-01, eccsoa012-02 back in service and drain eccsoa013-06 , eccsoa013-10 and eccsoa013-11 | APP-L2-EBS-DEPLOY
6 | 1hrs | 1 |  | Business will validate SITE A | Business
7 | 30 mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Keep required files into SITEB | APP-L2-ECOMM-MIDDLE-TIER
8 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | 1) Execute ./ecomsoa_deploy.sh on siteB(MT): putty to eccsoa013-06.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts <ENTER> ./ecomsoa_deploy.sh <ENTER> The deploy script will then run and it will take 10-20 minutes to complete. 2) Take eccsoa013-06, eccsoa013-10.int.westgroup.com and eccsoa013-11 out of MMode | APP-L2-EBS-DEPLOY
9 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Verify Deployment | APP-L2-ECOMM-MIDDLE-TIER
| 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | (optional) In case of any concerns, Bounce the servers as below: putty to eccsoa013-06.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts/ <ENTER> ./bounceServers.sh myacctsvcs_1000_20070123_prd_eccsoa013-06_1 myacctsvcs_1000_20070123_prd_eccsoa013-10_1 myacctsvcs_1000_20070123_prd_eccsoa013-11_1 <ENTER> This will kick off the script to bounce the servers. It may take ~20 min. to complete. | APP-L2-EBS-DEPLOY
10 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Undrain: -go to BIGIPadmin -search on myacctsvcs.int.westgroup.com -click edit all -put eccsoa013-06 and eccsoa013-11 back in service | APP-L2-EBS-DEPLOY
11 | 1hr |  |  | Business monitor changes on all servers | Business

## Backout Task DAY1
Step# | Estimated Duration | Node(s) Impacted | Server(s) | Step Details | Step Owner(s) and/or SM9 Group Name
1 | 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | Move required files to MT | APP-L2-ECOMM-MIDDLE-TIER
2 | 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | 3)Drain eccsoa010-12, eccsoa012-01 and eccsoa012-02 out of service (MT) -go to BIGIPadmin: -search on myacctsvcs.int.westgroup.com -click edit all -take eccsoa010-12, eccsoa012-01 and eccsoa012-02 out of service | APP-L2-EBS-DEPLOY
3 | 1hr | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | putty to eccsoa010-12.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts <ENTER> ./ecomsoa_deploy.sh <ENTER> The deploy script will then run and it will take 10-20 minutes to complete. | APP-L2-EBS-DEPLOY
4 | 30mins | 1 | eccsoa010-12.int.westgroup.com eccsoa012-01.int.westgroup.com eccsoa012-02.int.westgroup.com | Verify Deployment by checking the date of war file placed on the WAS deployment directory and notify APPLICATIONSUPPORT.EBS to perform next task | APP-L2-ECOMM-MIDDLE-TIER
5 | 30mins | 1 & 2 | eccsoa013-06.int.westgroup.com eccsoa013-11.int.westgroup.com eccsoa013-10.int.westgroup.com | Keep servers in Maintanence mode for 2hours and swap the drains 1) SwapServers -go to BIGIPadmin: -search on myacctsvcs.int.westgroup.com -click edit all -Keep eccsoa010-12, eccsoa012-01 and eccsoa012-02 back in service -take eccsoa013-06, eccsoa013-10 and eccsoa013-11 out of service | APP-L2-EBS-DEPLOY
7 | 30 mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Keep required files into SITEB | APP-L2-ECOMM-MIDDLE-TIER
8 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Execute ./ecomsoa_deploy.sh on siteB(MT): putty to eccsoa013-06.int.westgroup.com login as: appsupp Then type these exact commands: cd /home/photon_admn/resources/Ecommerce/scripts <ENTER> ./ecomsoa_deploy.sh <ENTER> The deploy script will then run and it will take 10-20 minutes to complete. | APP-L2-EBS-DEPLOY
9 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Verify Deployment (MT) | APP-L2-ECOMM-MIDDLE-TIER
10 | 30mins | 2 | eccsoa013-06.int.westgroup.com eccsoa013-11..int.westgroup.com eccsoa013-10.int.westgroup.com | Keep servers back in service(MT): go to BIGIPadmin -search on myacctsvcs.int.westgroup.com -click edit all -put eccsoa013-06, eccsoa013-10 and eccsoa013-11 back in service | APP-L2-EBS-DEPLOY